## Full Migration
Task Name | Responsible | Role | Status | Comments
Create DryRun project in Target Org (Must use migrated Process Template the Source Org).. Ex. Scrum-Modified-GH | Clark McBrayer
Run process to create Users from Source to Target Org | Clark McBrayer
Run FULL Migration process in GitHub Actions | Clark McBrayer |  |  | https://github.com/AIZ-GT/DevOps-Enablement-ADO-to-ADO-migration
Validate success. Check for errors and record counts |  |  |  | If errors or all items did not migrate, run PARTIAL Migraiton GitHub Action for specifiec Work Item types as needed. Repeat until satisfied all is migrated.
Copy AD Group users from GL to Global | Clark McBrayer
Insure correct AD Groups are set for each role |  |  |  | In some cases a different AD Group may be used during testing.
Turn over to Project Owner for validation. |  |  |  | If determined certain work items did not migrate, determine issue and run Partial Migration as needed.
Create/update new Service Connections as needed | Project owner / Helton's Team
Mike's script to ?????? |  |  |  | Ties service connections to pipelines
setting the Source project to RIM
If Partial migration is pregerred (item by item) see below steps
Repositories
* Service Connections
- If new or update Build and Release pipelines need migrating then we will need to pre-run this
Areas and Iterations
Teams
Work Item Querys
Variable Groups
Build Pipelines
Release Pipelines
* Task Group
- Task Groups are not being used so no need to run
Work-Items (Including 'Test Cases')
Groups
Test Configurations
Test Variables
Test Plans and Suites
Service Hooks
* Policies
- If new or updated policies are present will need to run the delete policies script prior to running
Dashboards
Delivery Plans
Artifacts
Copy AD Group users from GL to Global | Clark McBrayer
Turn over to Project Owner for validation. |  |  |  | If determined certain work items did not migrate, determine issue and run Partial Migration as needed.
Create/update new Service Connections as needed | Tom Whittemore / Helton's Team
Mike's script to ?????? |  |  |  | Ties service connections to pipelines
Any additional valideation running Pipelines with new Service Connections

## Elita remaining tasks
Task Name | Responsible | Date | Start time | End Time | Total Time | New or Update | Status | Comments
Run PARTIAL Migration process in GitHub Actions | Clark McBrayer | [6 empty] | https://github.com/AIZ-GT/DevOps-Enablement-ADO-to-ADO-migration
Repositories (this will delete repos, then re-migrate them ) |  | 2023-09-22 | 1:32PM | 1:56PM | 23m 57s
* Service Connections | [7 empty] | If new or update Build and Release pipelines need migrating then we will need to pre-run this
Areas and Iterations |  | 2023-09-19 | 2:48PM | 2:51PM | 3m 34s
Teams |  | 2023-09-20 |  |  | 36s
Work Item Querys |  | 2023-09-20 |  |  | 41s
Variable Groups |  | 2023-09-20 | 2:51PM | 2:52PM | 1m 10s
Build Pipelines |  | 2023-09-20 | 3:33PM | 3:36PM | 2m 30s
Release Pipelines |  | 2023-09-20 | 4:07PM | 4:09PM | 1m 29s
* Task Group (not used for Elita)
- Task Groups are not being used so no need to run
Work-Items (Including 'Test Cases') |  | 2023-09-21 |  |  | 6h 3m 38s |  |  | 9/20/2023 11h 51m 43s ---- 9/25/2023 6h 21m 11s ----- 9/26/2023 5h 43m 34s
Groups |  | 2023-09-21 | 1:20PM |  | 33m 50s
Test Configurations |  | 2023-09-21 | 2:11PM | 2:11PM | 31s
Test Variables |  | 2023-09-21 | 2:13PM | 2:14PM | 26s
Test Plans and Suites |  | 2023-09-21 | 2:16PM |  | 7h 4m 24s
Service Hooks |  | 2023-09-22 | 8:18AM | 8:19AM | 50s
* Policies (this will delete polices, then re-migrate them ) |  | 2023-09-22 | 3:08PM | 3:22PM | 14m 6 s
Dashboards |  | 2023-09-22 | 11:07AM | 11:08AM | 1m 8s
Delivery Plans |  | 2023-09-22 | 11:11AM | 11:11AM | 25s
Artifacts |  | 2023-09-25 |  |  | 11h 15m 26s |  |  | 2023-09-26
Validate success. Check for errors and record counts | [7 empty] | If errors or all items did not migrate, run PARTIAL Migraiton GitHub Action for specifiec Work Item types as needed. Repeat until satisfied all is migrated.
Copy AD Group users from GL to Global | Clark McBrayer
Insure correct AD Groups are set for each role | [7 empty] | In some cases a different AD Group may be used during testing.
Turn over to Project Owner for validation. | [7 empty] | If determined certain work items did not migrate, determine issue and run Partial Migration as needed.
Create/update new Service Connections as needed | Tom Whittemore / Helton's Team
Mike's script | [7 empty] | Ties service connections to pipelines
Any additional valideation running Pipelines with new Service Connections
setting the Source project to RIM